## Risk Register
Risk ID | Asset | Threat | Vulnerability | Impact(1-5) | Likelihood(1-5) | Risk Score | Risk Level | ISO 27001 Control | Existing Controls | Treatment | Treatment Action | Risk Owner | Status
R-001 | AWS Cloud Infrastructure | Unauthorized access through misconfigured S3 buckets | S3 buckets are not configured with proper access restrictions | 5 | 4 | 20 | Critical | A.5.23 Information security for use of cloud services | None | Mitigate | Restrict S3 bucket permissions and enable public access blocking | Cloud Operations Lead | Open
R-002 | PostgresSQL Database | Data Theft via SQL Injection Attacks | Application input validation is present, enabling SQL injection attacks. | 4 | 3 | 12 | High | A.8.8 Management of techinical vulnerabilities | None | Mitigate | Conduct code review and implement input validation on all database queries | Database Administrator | Open
R-003 | Microsoft 365 | Account takeover via phishing | Lack of MFA on employee accounts | 5 | 5 | 25 | Critical | A.8.5 Secure Authentication | Basic Spam Filtering | Mitigate | Enforce MFA on all Microsoft 365 accounts | CISO | Closed
R-004 | Employee Laptops | Data exposure from unsecured personal devices | No MDM solution to manager personal devices | 3 | 2 | 6 | Medium | A.8.1 User endpoint devices | None | Mitigate | Deploy MDM solution to enforce security policies on all employee devices | IT Admin | Open
R-005 | Payment Processing Application | Sensitive data exposure due to insecure API endpoints | API endpoints are exposed without proper encryption or authentication | 5 | 4 | 20 | Critical | A.8.24 Use of Cryptography | None | Mitigate | Implement TLS encryption and authentication controls on all API endpoints | Application Owner | In-Progress
R-006 | Customer PII data | Data breach caused by unauthorized access | Inadequate access control mechanisms for customer PII. | 4 | 3 | 12 | High | A.5.15 Access Control | None | Mitigate | Implement role based access control and conduct access reviews periodically | CISO | In-Progress
R-007 | Payment transaction records | Reputational damage resulting from a data breach | No monitoring or alerting for transaction records | 4 | 3 | 12 | High | A.5.24 Information security incident management planning and preparation | None | Mitigate | Develop and document a formal incident response plan | CISO | Open
R-008 | Employee credentials | System compromise due to password reuse | Lack of password policy enforcement | 3 | 2 | 6 | Medium | A.5.17 Authentication Information | None | Mitigate | Enforce password policy across organization | IAM Team | In-Progress
R-009 | Vendor & Third Party Contracts | Sensitive data exposure caused by third party security breach | Third party vendors are onboarded without reviewing their security practices | 4 | 3 | 12 | High | A.5.20 Addressing information security within supplier agreements | Basic contract with no security clause | Mitigate | Conduct vendor security assessments and include data protection clauses in contracts | Compliance Officer | Open
R-010 | Employees & End Users | Lack of cybersecurity awareness from staffs | Lack of awareness leads to phishing attacks, credential compromise and data leakage | 2 | 1 | 2 | Low | A.6.3 Information Security awareness, education and training | None | Accept | Provide security awareness training for employees | Human Resources | Closed

## Risk Matrix
Likelihood
|  | Rare | Unlikely | Possible | Likely | Certain
Impact | Negligible | Low | Low | Low | Low | Low
| Minor | Low | Low | Medium | Medium | Medium
| Moderate | Low | Medium | Medium | High | High
| Major | Low | Medium | High | High | Critical
| Severe | Low | Medium | High | Critical | Critical